## NAD Closed-Open
| NASA Planned Tasks |  |  |  | VIIRS NAD Closed | [11 empty] | VIIRS NAD OPEN
# | Task Name | Leads | Status | Report # | 2011-11-08 | 2011-11-09 | 2011-11-10 | 2011-11-14 | 2011-11-15 | 2011-11-16 | 2011-11-17 | 2011-11-18 | 2011-11-21 | Leads | Status | Report # | 2011-11-22 | 2011-11-23 | 2011-11-28 | 2011-11-29 | 2011-11-30 | 2011-12-01 | 2011-12-02 | 2011-12-05 | 2011-12-06 | 2011-12-07 | 2011-12-08 | 2011-12-09 | 2011-12-12 | 2011-12-13 | 2011-12-14 | 2011-12-15 | 2011-12-16 | 2011-12-19 | 2011-12-20 | 2011-12-21 | 2011-12-22 | 2011-12-23 | 2011-12-24 | 2011-12-26 | 2011-12-27 | 2011-12-28 | 2011-12-29 | 2011-12-30 | 2011-01-02 | 2011-01-03 | 2011-01-04 | 2011-01-05 | 2011-01-06 | 2011-01-09 | 2011-01-10 | 2011-01-11 | 2011-01-12 | 2011-01-13 | 2011-01-16 | 2011-01-17 | 2011-01-18 | 2011-01-19 | 2011-01-20
1 | FPF1: Noise measurement prior to RTA scanning | Alin, Tom | Open | [10 empty] | Alin, Tom | Open
2 | FPF2: Operability, Noise, SNR verification with nadir door closed | Alin, Tom | Open | [10 empty] | Alin, Tom | Open
3 | FPF3: In-scan aggregation verification – Non DNB bands | Jeff | Closed | NICST_REPORT_POST_11_003_agg_zone.ppt | [9 empty] | Jeff | Open
| FPF-4: Dual Gain transition verification | Jeff | Open | [10 empty] | Jeff | Open
4 | FPF5: On-board Bow-tie deletion verification | Jeff | Closed | NICST_REPORT_POST_11_001_bow_tie_deletion.ppt | [9 empty] | Jeff | Open
5 | FPF6: DC-restore functionality and performance check | Shihyan | Closed | NICST_REPORT_POST_11_002_DCR.pptx | [9 empty] | Shihyan | Open
6 | FPF7: Calibrator Visualization | Jeff, Ning | Open | [10 empty] | Jeff, Ning | Open
7 | CSE1: SD and SDSM characterization | Jon, Ning | Open | [10 empty] | Jon, Ning | Open
8 | CSE2: OBC Temperature Telemetry | Chengbo, Vincent | Open | [10 empty] | Chengbo, Vincent | Open
9 | CSE3: Stray light RSB SD analysis of non-polar SD data | Shihyan | Open | [10 empty] | Shihyan | Open
10 | CSE4: Temporal analysis of SD over polar region | Ning, Jon | Open | [10 empty] | Ning, Jon | Open
11 | CSE5: Temporal analysis of SD stability Monitor | Jon, Ning | Open | [10 empty] | Jon, Ning | Open
| RAD9: Cross-comaprison between VIIRS and MODIS | Aisheng, Xiong | Open | [10 empty] | Aisheng, Xiong | Open
RAD16: Moon in Space View
12 | RAD25: Dual Gain Anomaly Flagging | Ning | Open | [10 empty] | Ning | Open
| Tasks in Bold mean NASA responsibiliy | [12 empty] | Potential presentation

## Cryo-Door Open
Task Category | [11 empty] | VIIRS Cryo-Cooler Door Open
Cal/Val Coordination | Task ID | VTN Task IDs | Title | EOC Lead | ICV Lead | LTM/Ops Support Lead | Analysis Support Team | NASA Lead (s) | NASA Support(s) | Status | Report # | 2012-01-18 | 2012-01-19 | 2012-01-20 | 2012-01-21 | 2012-01-22 | 2012-01-23 | 2012-01-24 | 2012-01-25 | 2012-01-26 | 2012-01-31 | 2012-02-02 | 2012-02-07 | 2012-02-08 | 2012-02-09 | 2012-02-14 | 2012-02-16 | 2012-02-21 | 2012-02-23 | 2012-02-28 | 2012-03-01 | 2012-03-06 | 2012-03-08 | 2012-03-13
Functional Performance and Format (FPF) Evaluation | FPF-1 | 1105 | NOISE MEASUREMENT PRIOR TO RTA SCANNING | Florio | NA | NA | Schwarting, Tolea | Tolea | Schwarting
| FPF-2 | 718, 1036 | OPERABILITY, NOISE, SNR VERIFICATION WITH NADIR DOOR CLOSED | Florio | NA | NA | Schwarting, Tolea | Tolea | Schwarting
| FPF-3 | 747 | IN-SCAN AGGREGATION VERIFICATION – NON-DNB BANDS | NA | McIntire | NA | Moyer, Rausch | McIntire | ? | Open
| FPF-4 | 1041 | DUAL GAIN BAND AND DNB TRANSITION VERIFICATION | NA | Rausch | NA | Moyer, Christopher Florio, Lei | McIntire | Tolea | Open
| FPF-5 | 1020 | ON-BOARD BOW-TIE DELETION VERIFICATION | NA | McIntire | NA | Lee | McIntire | Lee | Open
| FPF-6 | 752. 755 | DC-RESTORE FUNCTIONALITY AND PERFORMANCE CHECK | NA | Jason Cardema | NA | Evan Haas, Lee | Lee | ? | Open
| FPF-7 | 762, 1165-1 | CALIBRATOR VISUAL INSPECTION | NA | Christopher Florio | NA | Lei | McIntire (TEB), Lei (RSB) | Wu, Wang | Open
Calibration System Evaluation (CSE) | CSE-1 | 1015 | SD AND SDSM CHARACTERIZATION | NA | Kameron Rausch | NA | DeLuccia, Xiong, Sun, Lei, McIntire | Fulbright | Lei | Open
| CSE-2 | 1017 | ONBOARD CALIBRATOR BLACK BODY (OBCBB) TEMPERATURE UNIFORMITY | NA | David Moyer | Changyong Cao | McIntire, Chiang, Xiong | C. Sun, Chiang | McIntire | Open | bar: 2012-01-24
| CSE-3 | 1042 | STRAYLIGHT VIIRS SRB SOLAR DIFFUSER STRAYLIGHT - ANALYSIS OF NON-POLAR SD DATA | NA | Juliette Costa | NA | Bicknell, Changbo, Lei | Lee | McItntire | Open | bar: 2012-01-24
| CSE-4 | 1166 | TEMPORAL ANALYSIS OF SD SIGNAL OVER POLAR REGION | NA | Kameron Rausch | NA | Lei, Changbo | Lei | Fulbright, Shihyan, Wang | Open | bar: 2012-01-24
| CSE-5 | 1167 | TEMPORAL ANALYSIS OF SOLAR DIFFUSER STABILITY MONITOR (SDSM) DATA | NA | De Luccia | Changyong Cao | Xiong, Lei, Bicknell | Fulbright | Lei, Efremova, McIntire, Wang | Open
| CSE-6 | 1046 | YAW MANEUVER ANALYSIS – SOLAR ATTENUATION SCREEN (SAS) TRANSMISSION | NA | Jack Xiong | NA | Sun, Rausch | McIntire, Efremova | J. Sun | Open
| CSE-7 | TBS | Yaw Maneuver: ANALYSIS OF SDSM DATA WITH MODEL ASSISTED EXTRAPOLATION OF SCREEN CALIBRATION DATA | NA | Jack Xiong | NA | Sun | McIntire, Efremova | J. Sun | Open |  | 2012-02-21: J. Sun; 2012-02-23: McIntire
Image Quality Evaluation (IMG) | IMG-1 | 753, 766, 1053 | CROSSTALK, ECHO, AND GHOST INVESTIGATION | NA | David Moyer | Changyong Cao | Lin, Schwarting, Lee, Oudrari, Chiang | Schwarting | Oudrari | Open
| IMG-2 | 760, 1055, 1050, 764, 768 | IMAGE ANALYSIS (STRIPING, GLINTS AND OTHER ARTIFACTS | NA | Chiang | Wu | Yuen, Wu, Lee, Oudrari | Chiang | Wu, Oudrari, Lee | Open
| IMG-3 | 763 | MOON ECHO AND GHOST CHECK | NA | Sun | Changyong Cao | Lin, Tolea | J. Sun | Schwarting, Oudrari, | Open
| IMG-4 | 1000, 1001 | LSF/MTF VALIDATION | NA | WolfeLin | NA | Lin | NA | NA | Open
Radiometric Evaluation (RAD) | RAD-1 | 1054, 767 | OUT-OF-BAND (OOB) SPECTRAL LEAKAGE (TEB) | NA | Moeller | NA | Schwarting, Costa | Schwarting | McIntire, Oudrari | Open
| RAD-2 | 1467 | CROSSTALK FROM EMISSIVE BANDS TO REFLECTIVE BANDS | NA | David Moyer | NA | Chiang, Schwarting | Schwarting | Chiang, Oudrari | Open
| RAD-3 | 757, 1039 | DYNAMIC RANGE AND LINEARITY | NA | McIntire (TEB), Lei (RSB) | NA |  | McIntire (TEB), Lei (RSB) | ? | Open
| RAD-4 | 765, 1048 | RESPONSE VS. SCAN ANGLE (RSB) | NA | Wu | Changyong Cao |  | Wu | C. Sun | Open
| RAD-5 | 955 | RELATIVE BAND-TO-BAND CALIBRATION ANALYSIS USING LUNAR DATA | NA | Sun | Changyong Cao, Xiong | Eplee | J. Sun | Lei, Oudrari | Open
| RAD-6 | 954 | RELATIVE BAND-TO-BAND CALIBRATION ANALYSIS USING SD DATA | NA | Lei | Changyong Cao |  | Lei | J. Sun, Oudrari | Open
| RAD-7 |  | SDR COMPARISON WITH MODEL | NA | Cao | Cao | Xiong, Wu | Xiong | Wu | Open
| RAD-8 | 1052, 1466 | SDR COMPARISON WITH AVHRR | NA | Cao | Cao | Xiong,Wu | Xiong | Wu | Open
| RAD-9 | 1051, 772 | SDR COMPARISON WITH MODIS | NA | Cao | Cao | Xiong, Wu, Oudrari | Xiong | Wu, Oudrari | Open | bar: 2012-01-24
| RAD-10 | 1040 | SRB RADIANCE/REFLECTANCE VALIDATION – RADIOMETRIC SITES | NA | De Luccia | Cao | Leisso | Xiong | Wu, Oudrari | Open
| RAD-11 | 1243 | M/T VALIDATION USING LAKE TAHOE SITE | NA | De Luccia | Cao | Hook | Xiong | Wu, Oudrari | Open
| RAD-12 | 956 | IN-BAND SPECTRAL RADIANCE COMPARISON WITH CRIS | NA | Moeller | Cao |  |  |  | Open
| RAD-13 | 774 | M/T SDR BAND-TO-BAND RADIOMETRIC COMPARISON | NA | De Luccia | NA | McIntire, Moyer, Hook | McIntire | ? | Open
| RAD-14 | 1386 | STRUCTURED SCENE ANALYSIS | NA |  |  |  | Lee | Oudrari | Open
| RAD-15 | 1019 | EMISSIVE BAND RESPONSE CHARACTERIZATION | NA | David Moyer | Cao | McIntire, Chiang, Wu | Efremova | McIntire, Wu, Chiang | Open |  | 2012-02-14: Efremova; 2012-02-21: Chiang
| RAD-16 | 771 | MOON IN SPACE VIEW CORRECTION | NA | Sun | Chiang | Tolea | J. Sun | Wang | Open
| RAD-17 | 1002 | BAND-TO-BAND REGISTRATION (BBR) VERIFICATION | NA | WolfeLin | Cao | Lin |  |  | Open
| RAD-18 | 1045 | SRB RADIANCE/REFLECTANCE VALIDATION – UNDERFLIGHTS | NA | Moeller | Cao |  |  |  | Open
| RAD-19 | 780, 1433 | LUNAR DATA ANALYSIS - ROLL MANEUVER | NA | Sun | Cao, Xiong | Eplee, Tolea | J. Sun | Wang | Open | bar: 2012-02-09
| RAD-20 | 957 | SPECTRAL VALIDATION USING HYPERSPECTRAL DATA FROM AIRCRAFT UNDERFLIGHTS | NA | Moeller | Cao |  |  |  | Open
| RAD-21 | 1465 | M/T RADIANCE VALIDATION WITH NAST-I AND MAS UNDERFLIGHTS | NA | Moeller | Cao |  |  |  | Open
| RAD-22 | 781 | ANALYSIS OF PITCH MANEUVER DATA (TEB RVS) | NA | Xiong, Wu | Cao | Moyer, De Luccia | Wu |  | Open |  | 2012-02-28: Wu; 2012-03-06: McIntire
| RAD-23 | 769, 770, 1388, 1393 | SDR REPROCESSING AND UPDATES | NA | De Luccia, Xiong | Cao | Chiang | Xiong | Chiang, Oudrari | Open
| RAD-24 | 1456, 0, 782 | SRB AND M/T SDR ACCURACY – PROVISIONAL AND VALIDATED LEVELS | NA | De Luccia, Xiong | Cao | Cardema, Haas | Xiong | McIntire, Lei, Chiang, Oudrari | Open
| RAD-25 |  | DUAL GAIN- TRANSITION & ANOMALY FLAGGING VERIFICATION | NA | Rausch | Cao | Lee, Oudrari | Lee | Oudrari | Open |  | 2012-02-14: Lee
Geometric Evaluation (GEO) | GEO-1 | 946 | INITIAL VALIDATION OF SC AUXILIARY EPHEMERIS AND ATTITUDE DATA |  | Wolfe | Cao | Nishihama, Cardema, Haas |  |  | Open
| GEO-2 | 945, 944 | INITIAL VALIDATION OF VIIRS ENCODER DATA, SCAN TIME, SCAN PERIOD, AND SCAN RATE STABILITY |  | Wolfe | Cao | Nishihama, Cardema, Haas |  |  | Open
| GEO-3 | 947 | ASSESS REASONABLENESS OF FIRST- PERIOD SDR GEOLOCATION |  | Wolfe | Cao | Nishihama |  |  | Open
| GEO-4 | 949 | BUILD FIRST-PERIOD SIMULATED VIIRS IMAGES FROM GCP CHIPS |  | Wolfe | Cao | Nishihama |  |  | Open
| GEO-5 | 948 | BUILD FIRST PERIOD VIIRS IMAGE CHIPS FROM SELECTED SDR PIXELS |  | Wolfe | Cao | Nishihama |  |  | Open
| GEO-6 | 950 | PERFORM FIRST PERIOD VIIRS SIMULATED IMAGE MATCH-UP |  | Wolfe | Cao | Nishihama |  |  | Open
| GEO-7 | 951 | ANALYZE FIRST PERIOD VIIRS GCP RESIDUALS |  | Wolfe | Cao | Nishihama |  |  | Open
| GEO-8 | 1110 | ANALYZE INITIAL INTRA-ORBIT THERMAL EFFECTS ON GEOLOCATION |  | Wolfe | Cao | Nishihama |  |  | Open
| GEO-9 | 952, 1109 | DEVELOP AND TEST INITIAL GEOLOCATION PARAMETER & THERMAL LUT UPDATES |  | Wolfe | Cao | Nishihama |  |  | Open
Preformance and Telemetry Trending (PTT) | PTT-1 | 1464, 1165-2, 746 | OPERABILITY, NOISE, SNR VERIFICATION | NA | Christopher Florio | Cao | Schwarting, Tolea | Tolea | Schwarting, Efremova | Open | bar: 2012-01-26
| PTT-2 | 746, 1043 | RDR HISTOGRAM ANALYSIS | NA | Christopher Florio | Cao | Changbo, Schwarting | C. Sun | Tolea | Open
| PTT-3 | 759, 1056 | NOISE AND SNR FOR UNIFORM EV SCENES | NA | Christopher Florio | Cao | Rausch, Tolea, Moyer | Tolea | Schwarting | Open
| PTT-4 |  | DNB OFFSET VERIFICATION | NA | Christopher Florio | Cao | Rausch |  | NA | Open
| PTT-5 | 958 | ELECTRONIC GAIN MEASUREMENT | NA | Christopher Florio | Cao | Lee | Lee | ? | Open
High priority
Low priority
NASA responsibility

## Issues Tracking
Issue # | Date | Authors | Title | Description | Status | Report name | Comments
1 | 2011-11-09 | Fulbright | SDSM profile issue | SDSM values in the OBCIP are showing abnormal profile. | Closed | sdsm_LP_all 11-10-2010 Jon.pdf | 11/11: Jon sent details to Frank, Luchalan et al. to see if a DR is needed. Initially root cause was assumed to be bit truncation. Discussion led to find that the "2s complement" used in the SDSM code is the real cause. The IDPS code was also found to read the RDR data in the wrong dectector/sample order.
2 | 2011-11-09 | Lei | M1 F-factot | M1 coefficients in the LUTs did not correct for red leaks observed during testing with SIS100. M1 F-factors are showing abour 30% change from pre-launch because of this red leak artifact. | Closed | VIIRS F-factor Preliminary Results.ppt | Need further discussion if LUTs need to be updated.
3 | 2011-11-09 | Chiang | OBCIP temperature | LUTs used to generated OBC temperature based on thermistors are not correct. | Closed | ND_3474488_VIIRS_Cal_report_NICSE_2011Nov10.ppt | Modified binary LUT of “VIIRS-SDR-BB-TEMP-COEFFS-LUT” has been generated by NICSE and delivered to CasaNOSA (Neal Baker) this morning.
4 | 2011-11-29 | Lee | Spikes in M4/M5 | Large spikes were observed in M4/M5 when looking at OBC. Gain transition is not as expected in some of the granules. | Closed |  | This is caused by band substitution during DNB band calibration. A code update had been done to exclude these data
5 | 2011-12-06 | Lee | DC offset change within the range | Data analysis has shown DCR offset change before reaching threshold. In some cases all detectors switches at the same time. | Open | ND_3474689_NICST_REPORT_POST_11_005_DCR_Cal_trending_slee.pptx | It was agreed that some DCR behaviors were not expected. Cause not known. It is assumed that there is no impact on SDR products.
6 | 2011-12-07 | Ning/Jon | VIIRS NIR Degradation | F-factors for M7, I2, M6 and M5 are showing high degradation with time. | Closed | Multiple reports | Degradation has been linked to the Tungsten Oxide contamination, resulting from Denton rework of the mirrors when usingthe ion gun (Tungsten filament).
7 | 2012-01-20 | Tolea Schwarting C. Sun | Bad scan: Fill values | Scan data have fill values: /npp/ndata5/NICSE/archive/VIIRS/sd3e/DailyIngest/20120119/OBC/IVOBC_npp_d20120119_t0544495_e0546136_b01175_c20120119103355516674_noaa_ops.h5. scan 33: M2, M3 and M5 | Open |  | There are fill values (65534 = MISS_UINT16_FILL) All the other telemetries have fill values as well for that scan. The telemetry trending kicked out these scans.
8 | 2012-01-31 | McIntire/ Efremova/Chiang | M13 wrong calibration | M13 low gain radiances are not properly calibrated. High gain SV background values are used instead of low gain ones. | Closed | ND_3475038_NICST_REPORT_POST_12_004_m13_lg_code.pdf | A DR was generated by NICSE on 01/31/2012, to intiate the process for IDPS operational code correction. Fix was made and tested by the NASA team. Corrected code and test results were sent to DPE for verification and implmentation into the operational stream.
9 | 2012-02-09 | McIntire/Efremova/Anderson/ Chiang | M13 aggregation issue | M13 is a dual gain that is aggregated by IDPS. Team was first to discover that the aggregatation performed by SDR code is done in temperature space instead of the radiance space. | Open | NICST_REPORT_POST_12_005_m13_agg_code_v2.pdf | Team has generated a DR, and has provided support to change the code to perform aggregation in the radiance space. The corrected code was verified sinf internal offline SDR processing and is being made available to DPE for further testing in preparation for implementation in the operational stream.
10 | 2012-02-22 | McIntire/C. Sun/Efremova/ Chiang | M13 bad scans | M13 showing multiple granules with bad scans. This oculd be related to the issue of dual gain bit stuck in HG for 4 scans, leading to bad calibration. | Closed |  | McIntire et al. investiigated this issue and has confirmed the dual gain issue is as th e root-cause. Seems like a DR was already issued. A DR was created (DR 4620) on 03-06-2012