## Tasks 08-16-2011
NPP VIIRS SDR Cal/Val Task Assignments | [10 empty] | See color code at the bottom
Dr. Frank J. De Luccia
Date of Last Revision: |  |  | 2011-05-16
Geo-related tasks modified by R Wolfe, 5/25/2011
Radiometric tasks modified by Jack Xiong, 5/25/2011
Task Category | Task ID | VTN Task IDs | Title | EOC Lead | ICV Lead | LTM/Ops Support Lead | Analysis Support Team | NASA Lead (s) | NASA Support(s) | Task Description Released (Y/N) | % Tool Readiness | Tool on Server (Y/N) | Priority | NASA Comments | Essential for Provisional Maturity at Activation + 90d | July/August Rehearsal - Demo or Description?
Cal/Val Coordination | [5 empty] | Cao, De Luccia, Xiong, Oudrari, Moyer, Wolfe
Functional Performance and Format (FPF) Evaluation | FPF-1 | 1105 | NOISE MEASUREMENT PRIOR TO RTA SCANNING | Florio | NA | NA | Schwarting, Tolea | Tolea | Schwarting | Y | 100% |  | M |  | YES | DEMO
| FPF-2 | 718, 1036 | OPERABILITY, NOISE, SNR VERIFICATION WITH NADIR DOOR CLOSED | Florio | NA | NA | Schwarting, Tolea | Tolea | Schwarting | Y | 80% |  | M |  | YES | DEMO
| FPF-3 | 747 | IN-SCAN AGGREGATION VERIFICATION – NON-DNB BANDS | NA | McIntire | NA | Moyer, Rausch | McIntire | ? | Y | 100% | Y | H |  | YES | DEMO
| FPF-4 | 1041 | DUAL GAIN BAND AND DNB TRANSITION VERIFICATION | NA | Rausch | NA | Moyer, Christopher Florio, Lei | Tolea | McIntire | Y | 75% | Y | M |  | YES | DEMO
| FPF-5 | 1020 | ON-BOARD BOW-TIE DELETION VERIFICATION | NA | McIntire | NA | Lee | McIntire | Lee | Y | 100% | Y | H |  | YES | DEMO
| FPF-6 | 752. 755 | DC-RESTORE FUNCTIONALITY AND PERFORMANCE CHECK | NA | Jason Cardema | NA | Evan Haas, Lee | Lee | ? | Y | 80% | Y | M |  | YES | DEMO
| FPF-7 | 762, 1165-1 | CALIBRATOR VISUAL INSPECTION | NA | Christopher Florio | NA | Lei | McIntire (TEB), Lei (RSB) | Wu | Y | 80% | Y | M |  | YES | DEMO
Calibration System Evaluation (CSE) | CSE-1 | 1015 | SD AND SDSM CHARACTERIZATION | NA | Kameron Rausch | NA | DeLuccia, Xiong, Sun, Lei, McIntire | Fulbright | Lei | Y | 90% | Y | H |  | YES | DESCRIPTION
| CSE-2 | 1017 | ONBOARD CALIBRATOR BLACK BODY (OBCBB) TEMPERATURE UNIFORMITY | NA | David Moyer | Changyong Cao | McIntire, Chiang, Xiong | C. Sun | McIntire | Y | 80% | Y | H |  | YES | DEMO
| CSE-3 | 1042 | STRAYLIGHT VIIRS SRB SOLAR DIFFUSER STRAYLIGHT - ANALYSIS OF NON-POLAR SD DATA | NA | Juliette Costa | NA | Bicknell, Changbo, Lei | Lee | McItntire | Y | 80% | Y | M |  | NO | DESCRIPTION
| CSE-4 | 1166 | TEMPORAL ANALYSIS OF SD SIGNAL OVER POLAR REGION | NA | Kameron Rausch | NA | Lei, Changbo | Lei | Fulbright | Y | 85% | Y | H |  | YES | DEMO
| CSE-5 | 1167 | TEMPORAL ANALYSIS OF SOLAR DIFFUSER STABILITY MONITOR (SDSM) DATA | NA | De Luccia | Changyong Cao | Xiong, Lei, Bicknell | Fulbright | Lei | Y | 90% | Y | H |  | YES | DEMO
| CSE-6 | 1046 | YAW MANEUVER ANALYSIS – SOLAR ATTENUATION SCREEN (SAS) TRANSMISSION | NA | Jack Xiong | NA | Sun, Rausch | McIntire | J. Sun | Y | 70% |  | H |  | YES | DESCRIPTION
| CSE-7 | TBS | Yaw Maneuver: ANALYSIS OF SDSM DATA WITH MODEL ASSISTED EXTRAPOLATION OF SCREEN CALIBRATION DATA | NA | Jack Xiong | NA | Sun | McIntire | J. Sun | Y | 70% |  | H |  | NO | DESCRIPTION
Image Quality Evaluation (IMG) | IMG-1 | 753, 766, 1053 | CROSSTALK, ECHO, AND GHOST INVESTIGATION | NA | David Moyer | Changyong Cao | Lin, Schwarting, Lee, Oudrari, Chiang | Schwarting | Oudrari | N | 20% |  | M |  | YES | DEMO
| IMG-2 | 760, 1055, 1050, 764, 768 | IMAGE ANALYSIS (STRIPING, GLINTS AND OTHER ARTIFACTS | NA | Chiang | Wu | Yuen, Wu, Lee, Oudrari | Chiang | Wu, Oudrari, Lee | Y | 100% | Y | H |  | YES | DEMO
| IMG-3 | 763 | MOON ECHO AND GHOST CHECK | NA | Sun | Changyong Cao | Lin, Tolea | J. Sun | Schwarting, Oudrari, | Y | 80%? |  | H |  | YES | DESCRIPTION
| IMG-4 | 1000, 1001 | LSF/MTF VALIDATION | NA | WolfeLin | NA | Lin | NA | NA | N |  |  |  |  | NO | DESCRIPTION
Radiometric Evaluation (RAD) | RAD-1 | 1054, 767 | OUT-OF-BAND (OOB) SPECTRAL LEAKAGE (TEB) | NA | Moeller | NA | Schwarting, Costa | Schwarting | McIntire, Oudrari | Y | 20% |  | L |  | YES | DESCRIPTION
| RAD-2 | 1467 | CROSSTALK FROM EMISSIVE BANDS TO REFLECTIVE BANDS | NA | David Moyer | NA | Chiang, Schwarting | Schwarting | Chiang, Oudrari | N | 50% |  | M |  | YES | DESCRIPTION
| RAD-3 | 757, 1039 | DYNAMIC RANGE AND LINEARITY | NA | McIntire (TEB), Lei (RSB) | NA |  | McIntire (TEB), Lei (RSB) |  | Y | 80% | Y | H |  | YES | DESCRIPTION
| RAD-4 | 765, 1048 | RESPONSE VS. SCAN ANGLE (RSB) | NA | Wu | Changyong Cao |  | Wu | C. Sun | Y | 60% |  | H |  | YES | DEMO
| RAD-5 | 955 | RELATIVE BAND-TO-BAND CALIBRATION ANALYSIS USING LUNAR DATA | NA | Sun | Changyong Cao, Xiong | Eplee | J. Sun | Lei, Oudrari | Y | 50% |  | H |  | NO | DESCRIPTION
| RAD-6 | 954 | RELATIVE BAND-TO-BAND CALIBRATION ANALYSIS USING SD DATA | NA | Lei | Changyong Cao |  | Lei | J. Sun, Oudrari | Y | 85% |  | H |  | NO | DESCRIPTION
| RAD-7 |  | SDR COMPARISON WITH MODEL | NA | Cao | Cao | Xiong, Wu | Xiong | Wu | NA | NA |  | NA |  | YES | DESCRIPTION
| RAD-8 | 1052, 1466 | SDR COMPARISON WITH AVHRR | NA | Cao | Cao | Xiong,Wu | Xiong | Wu | N | 50% |  | L |  | YES | DESCRIPTION
| RAD-9 | 1051, 772 | SDR COMPARISON WITH MODIS | NA | Cao | Cao | Xiong, Wu, Oudrari | Xiong | Wu, Oudrari | Y | 60% |  | H |  | YES | DESCRIPTION
| RAD-10 | 1040 | SRB RADIANCE/REFLECTANCE VALIDATION – RADIOMETRIC SITES | NA | De Luccia | Cao | Leisso | Xiong | Wu, Oudrari | N | 50% |  | L |  | YES | DESCRIPTION
| RAD-11 | 1243 | M/T VALIDATION USING LAKE TAHOE SITE | NA | De Luccia | Cao | Hook | Xiong | Wu, Oudrari | N | 20% |  | L |  | YES | DESCRIPTION
| RAD-12 | 956 | IN-BAND SPECTRAL RADIANCE COMPARISON WITH CRIS | NA | Moeller | Cao |  |  |  | N |  |  |  |  | YES | DESCRIPTION
| RAD-13 | 774 | M/T SDR BAND-TO-BAND RADIOMETRIC COMPARISON | NA | De Luccia | NA | McIntire, Moyer, Hook | McIntire | ? | N | 20% |  | M |  | YES | DESCRIPTION
| RAD-14 | 1386 | STRUCTURED SCENE ANALYSIS | NA |  |  |  | Lee | Oudrari | N | 20% |  | L |  | YES | NA
| RAD-15 | 1019 | EMISSIVE BAND RESPONSE CHARACTERIZATION | NA | David Moyer | Cao | McIntire, Chiang, Wu | Efremova | McIntire, Wu, Chiang | Y | 80% |  | H |  | YES | DESCRIPTION
| RAD-16 | 771 | MOON IN SPACE VIEW CORRECTION | NA | Sun | Chiang | Tolea | J. Sun | Tolea | Y | 100% |  | H |  | YES | DEMO
| RAD-17 | 1002 | BAND-TO-BAND REGISTRATION (BBR) VERIFICATION | NA | WolfeLin | Cao | Lin |  |  | N |  |  |  |  | YES | DESCRIPTION
| RAD-18 | 1045 | SRB RADIANCE/REFLECTANCE VALIDATION – UNDERFLIGHTS | NA | Moeller | Cao |  |  |  | N |  |  |  |  | YES | UNFUNDED - DEFERRED
| RAD-19 | 780, 1433 | LUNAR DATA ANALYSIS - ROLL MANEUVER | NA | Sun | Cao, Xiong | Eplee, Tolea | J. Sun | Tolea | Y | 50% |  | H |  | YES | DESCRIPTION
| RAD-20 | 957 | SPECTRAL VALIDATION USING HYPERSPECTRAL DATA FROM AIRCRAFT UNDERFLIGHTS | NA | Moeller | Cao |  |  |  | N |  |  | H |  | YES | UNFUNDED - DEFERRED
| RAD-21 | 1465 | M/T RADIANCE VALIDATION WITH NAST-I AND MAS UNDERFLIGHTS | NA | Moeller | Cao |  |  |  | N |  |  | H |  | YES | UNFUNDED - DEFERRED
| RAD-22 | 781 | ANALYSIS OF PITCH MANEUVER DATA (TEB RVS) | NA | Xiong, Wu | Cao | Moyer, De Luccia | Wu |  | Y | 60% |  | H |  | YES | DESCRIPTION
| RAD-23 | 769, 770, 1388, 1393 | SDR REPROCESSING AND UPDATES | NA | De Luccia, Xiong | Cao | Chiang | Xiong | Chiang, Oudrari | N |  |  | H |  | YES | DESCRIPTION
| RAD-24 | 1456, 0, 782 | SRB AND M/T SDR ACCURACY – PROVISIONAL AND VALIDATED LEVELS | NA | De Luccia, Xiong | Cao | Cardema, Haas | Xiong | McIntire, Lei, Chiang, Oudrari | N |  |  | H |  | YES | DESCRIPTION
| RAD-25 |  | DUAL GAIN ANOMALY FLAGGING VERIFICATION | NA | Rausch | Cao | Lee, Oudrari | Lee | Oudrari | Y | 100% | Y | M |  | NO | TBD
Geometric Evaluation (GEO) | GEO-1 | 946 | INITIAL VALIDATION OF SC AUXILIARY EPHEMERIS AND ATTITUDE DATA |  | Wolfe | Cao | Nishihama, Cardema, Haas | [7 empty] | YES | DESCRIPTION
| GEO-2 | 945, 944 | INITIAL VALIDATION OF VIIRS ENCODER DATA, SCAN TIME, SCAN PERIOD, AND SCAN RATE STABILITY |  | Wolfe | Cao | Nishihama, Cardema, Haas | [7 empty] | YES | DESCRIPTION
| GEO-3 | 947 | ASSESS REASONABLENESS OF FIRST- PERIOD SDR GEOLOCATION |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DEMO
| GEO-4 | 949 | BUILD FIRST-PERIOD SIMULATED VIIRS IMAGES FROM GCP CHIPS |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DEMO
| GEO-5 | 948 | BUILD FIRST PERIOD VIIRS IMAGE CHIPS FROM SELECTED SDR PIXELS |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DEMO
| GEO-6 | 950 | PERFORM FIRST PERIOD VIIRS SIMULATED IMAGE MATCH-UP |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DEMO
| GEO-7 | 951 | ANALYZE FIRST PERIOD VIIRS GCP RESIDUALS |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DEMO
| GEO-8 | 1110 | ANALYZE INITIAL INTRA-ORBIT THERMAL EFFECTS ON GEOLOCATION |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DESCRIPTION
| GEO-9 | 952, 1109 | DEVELOP AND TEST INITIAL GEOLOCATION PARAMETER & THERMAL LUT UPDATES |  | Wolfe | Cao | Nishihama | [7 empty] | YES | DESCRIPTION
Preformance and Telemetry Trending (PTT) | PTT-1 | 1464, 1165-2, 746 | OPERABILITY, NOISE, SNR VERIFICATION | NA | Christopher Florio | Cao | Schwarting, Tolea | Tolea | Schwarting | Y | 80% |  | M |  | YES | DESCRIPTION
| PTT-2 | 746, 1043 | RDR HISTOGRAM ANALYSIS | NA | Christopher Florio | Cao | Changbo, Schwarting | C. Sun | Tolea | Y | 70% | Y | M |  | YES | DESCRIPTION
| PTT-3 | 759, 1056 | NOISE AND SNR FOR UNIFORM EV SCENES | NA | Christopher Florio | Cao | Rausch, Tolea, Moyer | Tolea | Schwarting | Y | 50% |  | M |  | YES | DESCRIPTION
| PTT-4 |  | DNB OFFSET VERIFICATION | NA | Christopher Florio | Cao | Rausch |  | NA | NA | NA |  |  |  | YES | DESCRIPTION
| PTT-5 | 958 | ELECTRONIC GAIN MEASUREMENT | NA | Christopher Florio | Cao | Lee | Lee | ? | Y | 100% | Y | M |  | YES | DESCRIPTION
[11 empty] | Ready |  | L
[11 empty] | Not quite ready |  | M
[11 empty] | Not ready |  | H

## VTN Readiness Criteria
•Task owner for each plan has developed detailed execution plan, including identification or definition of:
–Prerequisite tasks
–Inputs
–Data processing and analysis methodologies
–Execution tools
–Output products
–Timelines
–Reporting schedule
–Inter-team interaction plans and schedule
–Task completion criteria
–Required documentation, including plan for capture and archival of findings

## Assignees
Needs to be updated
Name | Org. | Lead | Support
Chiang | NICSE | CSE-2, IMG-2, RAD-2, RAD-15
Fulbright | NICSE |  | CSE-1
Lee | NICST |  | FPF-5, FPF-6, CSE-3, IMG-1, IMG-2, RAD-25, PTT-5
Lei | NICSE | RAD-3, RAD-6 | FPF-4, FPF-7, CSE-1, CSE-4, CSE-5,
McIntire | NICST | FPF-3, FPF-5, CSE-2, RAD-3, RAD-13, RAD-15 | FPF-7, CSE-3, CSE-1
Schwarting | NICST | FPF-2, PTT-1 | IMG-1, RAD-1, RAD-2, RAD-14
Sun | MCST | CSE-6, CSE-7, IMG-3, RAD-5, RAD-16, RAD-19 | CSE-1
Tolea | NICST |  | FPF-1, FPF-2, IMG-3, RAD-16, RAD-19, PTT-1, PTT-3
Wu | NICSE | IMG-2, RAD-4, RAD-22 | RAD-8, RAD-9, RAD-15
Xiong | NASA | FPF-7, CSE-1, CSE-4, CSE-5, CSE-6, CSE-7, RAD-8, RAD-9, RAD-22, RAD-23, RAD-24
Oudrari | PSG |  | IMG1-3, RAD1-2, RAD9-11, RAD-14, RAD-23, RAD-25